## Sheet1
Tasks needed 6 to 14 months prior to event/program | Assigned to | Date Assiged | Date Needed | Completed
Determine the goal and need for the event
Define the event
Select Name & Determine Theme
Develop Budget. Must be submitted by October of previous year for consideration. i.e. Event is in August 2019. Budget for event must be submitted by October 2018.
Set Date, time, and location
Assess Manpower needs
Recruit Volunteer Committee
Create contact list with phone number and email
Work with Staff Advisor to create event folder on the server
Tasks needed 3 to 6 months prior to event/program | Assigned to | Date Assiged | Date Needed | Completed
Set up online event registration
Create and get approved a promotional flyer
Visit event location to determine needs
Set schedule for committee meetings
Acquire contracts for location, vendors, etc.
Develop Promotional plan (roundtables, mailers, in person presentations, etc.)
Tasks needed 1 to 3 months prior to event/program | Assigned to | Date Assiged | Date Needed | Completed
Create news release for event
Promote event through Social Media channels
Determine event/activity safety needs
Select and order awards/trophies
Order event patches
Order banners and signs
Order program supplies for event / Make purchases
Tasks needed 2 weeks prior to event/program | Assigned to | Date Assiged | Date Needed | Completed
Confirm with volunteers
Confirm with location/vendors/etc.
Prepare any final documentation
Meet with chair and staff to finalize plans
Request petty cash
Tasks needed 1 week prior to event/program | Assigned to | Date Assiged | Date Needed | Completed
Confirm # attending
Finalize registration materials
Hold one final walk through
Get petty cash
Get a money bag/box and receipt book(s) from Council
Creat an evaluation/assessment for the evnt
Day before event | Assigned to | Date Assiged | Date Needed | Completed
Set up event headquarters
Pack up all needed equipment and supplies
Day of event | Assigned to | Date Assiged | Date Needed | Completed
Arrive early to unpack supplies, equipment, etc.
Set up registration area
Set up program areas
Review details with Volunteers
Greet guests
Registration/Check-In
Oversee event to ensure smooth execution
Tear down and clean up site
Post Event/Activity | Assigned to | Date Assiged | Date Needed | Completed
Turn in all cash payments to the Council
Turn in all vendor invoices and packing slips
Turn in receipts for purchases made. Mark the receipts with the appropriate PO Number
Turn in any unused Petty Cash, receipts, and a recap form
Turn in any Gift In Kind forms
Send thank you letters
Host evaluation meeting with committee and volunteers to discuss program - take notes for next year
Complete a Final Activity Report
Complete a Closing Report Form
Closing out the Activity (include recommended budget for next year)
Ensure that staff advisor has copies of all documents saved in Activity/Event Folder